## Callington
Action Number | Endorsed Action | Endorsed Timeframe | Status as of February 2023 | Comment
1 | Advocate and support the continued protection of heritage places, monuments, cemetery and the Historic Conservation Area. | Ongoing | Commenced | Ongoing through Council business as usual. Notably, State Heritage listing of Callington Smelter occurred post the endorsement of the Plan. Council seek grant for improved fencing and signage around the Callington Smelter.
2 | Celebrate indigenous and european heritage and culture of the area through initiatives such as interpretive signage, public art and the materials chosen for public realm improvements. Input from local artists should be encouraged. | Ongoing | Not Commenced
3 | Continually inform and facilitate community information sessions on planning and development of Local Heritage Places and the Historic Conservation Area including accessing the Heritage Incentive Scheme. | Ongoing | Commenced | Business as usual through a range of Council departments.
4 | Reinforce detached dwellings on large allotments. | Ongoing | Completed | Council successfully embedded this priority with the South Australian Planning and Design Code.
5 | Improve the appearance of township entrances and approaches. Develop gateway treatments that reflect the local sense of place and heritage. | Medium | Not Commenced
6 | Improve and enhance the Heritage Walk through the township identifying local and state heritage listed properties of interest. | Short | Not Commenced
7 | Continue to support the role and function of community and sporting groups, acknowledging the important role they play to encourage social interaction and inclusion. | Ongoing | Commenced | Ongoing through Council business as usual.
8 | Continue to support local community events which provide an opportunity for the community to come together and which helps to cement the identity of the town and creates a sense of community. | Ongoing | Commenced | Ongoing through Council business as usual.
9 | Advocate for a broader range of in-home services and transport to operate throughout the town in coordination with the Rural City of Murray Bridge so that the elderly and disabled can continue to remain within the Callington community. | Short | Commenced | Ongoing as business as usual, MBDC and Rural Council of Murray Bridge.
10 | Provide information to the Callington community on the housing support services available throughout the district, connecting those experiencing housing difficulties with the appropriate services. | Short | Commenced | Ongoing through business as usual.
11 | Continue to provide facilities which cater for informal recreation activities to engage younger residents and support community groups which perform this role. | Ongoing | Commenced | Pump Track and Court Renewal completed. Dirt Pump Track (Community Grant funded) completed. Partial renewal of playground completed.
12 | Where possible support the role, function and growth of the Callington Primary School and Callington Kindergarten to continue to provide desirable local education options for the town. | Ongoing | Commenced | Ongoing through Council business as usual.
13 | Finalise design and implement a dedicated pedestrian access across the Bremer River improving pedestrian links to both sides of the township. | Short - Medium | Commenced | Refer to Council Report August 2022 for update.
14 | Establish improved pedestrian links and direct connectivity along the Bremer River/Murray Street reserve with the focus on achieving improved access links to the recreation grounds and school. | Medium | Not Commenced
15 | Review footpath infrastructure on Callington Road, Montefiore Street, Murray Street, Bridge Street and East Terrace and undertake footpath upgrades where necessary. | Short - Medium | Commenced | District-wide audit undertaken. To be implemented through the Footpath Program where necessary.
16 | Establish a pedestrian crossing between the primary school and recreation grounds on Callington Road. | Short - Medium | Not Commenced
17 | Advocate for improved public transport services and associated infrastructure for the township. | Ongoing | Commenced | Ongoing through business as usual.
18 | Improve provision of open space furniture (e.g. seating, shelter) within Murray Street/Steele Road/Hefford Drive reserves (adjacent the Bremer River) including integrated interpretive signage. | Short | Not Commenced
19 | Develop trail connections and activation from Callington Oval to the Bremer River and the township through strategic land/tenure acquisition or protected verge trails/footpaths. | Short - Medium | Not Commenced
20 | Promote additional and appropriate tree plantings within the recreation grounds and linear reserves. | Short | Commenced | Strategic tree plantings undertaken where appropriate and where opportunities present.
21 | Undertake re-vegetation and weed management of reserve areas adjacent the Bremer River sensitive to its biology in conjunction with environmental community groups. | Short - Medium | Not Commenced
22 | Advocate and support funding to go to community and recreation infrastructure projects within Callington in collaboration of the Kanmantoo Callington Community Consultative Committee (KCCCC) Masterplan. | Ongoing | Commenced | Ongoing through Council business as usual.
23 | Investigate options for recycled water usage for re-vegetation projects and greening for Callington. | Ongoing | Not Commenced | Not progressed.
24 | Undertake staged improvements to the Callington Recreation Grounds, including: • Re-development and construction of a new community hub • Construction of a small amenities/toilet building for the second (cricket) oval | Short and Medium | Commenced | Community Hub Building completed and fully operational. Second amenities building not programmed to be constructed but staff understand this remains a priority for the Recreation Grounds.
25 | Create and enhance activity opportunities linked to the Callington Oval surrounds including a focus on children, youth and families (BMX/pump track, skate park, dog park play, picnic), trail links and promote shared use of the Callington Primary School where possible. | Short - Medium | Completed | Pump Track and Court Renewal completed. Dirt Pump Track (Community Grant funded) completed. Partial renewal of playground completed.
26 | Continue to promote and support the Callington Recreation Oval and Memorial Hall as community, recreation and event facilities within the township. | Ongoing | Commenced | Ongoing through Council business as usual. Council financially contributed to a current lighting upgrade project.
27 | Review existing planning control and zoning of recreation grounds with an aim to better define, maintain and improve future growth of the recreation grounds. | Short - Medium | Completed | Review of South Australian Planning and Design Code policy undertaken. No further action deemed necessary.
28 | Promote continued archaeological investigations and their protection at the Recreation Grounds. | Ongoing | Commenced | Ongoing discussions with relevant key stakeholders to ensure protection. Callington Smelter now a listed State Heritage item with future plans to improve protection of this heritage fabric. Council to seek grant funding to assist with improved protection of the Callington Smelter.
29 | Conduct a strategic review of existing infrastructure and current zoning of land surrounding Callington to promote opportunities for employment in horticultural and agriculture industries. | Short | Commenced | Council engaged with the State Government regarding the development of the GARP.
30 | Promote development within the existing Local Centre Zone as being the focus of retail and commercial development within the township as well as promoting accessibility of nearby employment lands. | Ongoing | Commenced | Ongoing as business as usual, MBDC and Rural Council of Murray Bridge.
31 | Investigate potential for re-alignment of the Local Government Boundary of Mount Barker and Murray Bridge Council’s to contain the Callington Township in its entirety. | Medium | Not Commenced
32 | Continue to support and promote tourism (especially heritage tourism) and events within the township while seeking additional opportunities for new events both within the township and in adjacent areas. | Ongoing | Not Commenced | Ongoing support through Community Development and the Tourism and Events Department.
33 | Establish a short-term accommodation in the form of an RV Park on Council-owned land and following implementation investigate expansion and commercialisation opportunities. | Short | Completed | Project completed and successfully operational.
34 | Establish and delineate a pedestrian footpath along Montefiore Street between Murray Street and North Terrace with integrated street furniture, lighting and street tree plantings. | Medium | Not Commenced
35 | Investigate further activation opportunities (creation of an activity node or similar) on and/or adjacent to the main street. | Short - Medium | Not Commenced
36 | Establish identification and heritage signage promoting the main street and heritage properties within the township/region. | Short | Not Commenced
37 | Actively promote existing and future commercial development within the main street locality. | Ongoing | Not Commenced | Ongoing through business as usual.
38 | Undertake a review of existing kerb, gutter, pedestrian footpaths, lighting, street furniture and storm water management so-as to inform infrastructure upgrades for well-used and strategic corridors within the township with a focus on North Terrace, Callington Road, Montefiore Street, Murray Street and East Terrace. | Short | Commenced | Review of footpath undertaken. Footpath improvements prioritised throughout the District via the Footpath Program.
39 | Investigate the potential for establishing a CWMS to service the township. | Medium | Not Commenced | Investigations undertaken with relevant internal and external stakeholders. Not planned to be prioritised at this point in time.
40 | Investigate the potential to increase recycled water infrastructure within the township and surrounding agricultural region. | Short | Not Commenced
41 | Review storm-water management and implement small-scale storm-water infrastructure upgrades in identified issue areas for example the swale next to the Recreation Ground oval. | Medium | Not Commenced
42 | Continue working with the CFS to ensure Bushfire Management Plans are up-to-date. | Ongoing | Commenced | Ongoing through Council business as usual.