## Echunga
Action Number | Endorsed Action | Endorsed Timeframe | Status as of February 2023 | Comment
1 | Recognise the identity of the Echunga Township by acknowledging and supporting both social and recreational activities which support the creation of a cohesive and inclusive local community. | Ongoing | Commenced | Continued support for Community events such as the All British Day, supporting local sporting teams through the provision of facilities and infrastructure through the Recreation Ground management committee.
2 | Support the creation and implementation of both Council and industry led strategies to better recognise and support the many local businesses and rural enterprises which help to define the Echunga Township and it surrounds, including the equine industry. | Medium | Not Commenced | Council's new economic development resource will investigate the delivery of this action by engaging with local business owners and industry leaders to better understand the economic conditions and issues facing local business.
3 | Implement strategies to improve the arrival into the town, providing signage and entrance statements to more clearly define historic character and entrances into the town. | Short | Not Commenced | Council is currently working on a project to design to entrance corridors, entry statements and signage for Mount Barker. The design elements delivered through this project with then set a District wide standard for the design of township entrance statements and signage. Once the design standard is established this project can then be initiated throughout other townships throughout the District. Council will seek to engage with the wider Mount Barker District on the development of these design standards.
4 | Provide more appropriate zoning for areas of the township currently within the Primary Production Zone as to better reflect its use e.g. primary school, golf course and recreation ground. | Medium | Not Commenced | The action requires Council to consider a Code Amendment under then State planning legislation. Council will be developing a Code amendment program during the 2023/24 FY.
5 | Celebrate both Peramangk and European heritage and culture of the town and its rural surrounds through initiatives such as interpretive signage and public art displays. | Ongoing | Commenced | Council currently works with Peramangk elders to better understand the indigenous significance of the Battunga Country to the township and will seek to represent this in projects such as the entrance statement signage. Council has recently employed an arts officer who will further consider the delivery of this action as part of the District wide Art Strategy recently endorsed by Council.
6 | Continue to recognise and preserve the town’s historic buildings, providing policy frame work for the retention and protection of these important building whilst also providing fi financial support to property owners through the continuation of Council’s heritage incentive scheme. | Ongoing | Commenced | Council currently maintains a Heritage Incentive Scheme which provides small grants for owners of heritage buildings to make improvements their buildings. Council also offers free professional advice on the maintenance and upgrade of heritage buildings.
7 | Continue to support the role and function of community and sporting groups, acknowledging the important role they play to encourage social interaction and inclusion. | Ongoing | Commenced | Council supports local sporting teams through the provision of facilities and infrastructure working with the Recreation Ground management committee. A recent project has included the resurfacing and netball courts.
8 | Continue to support local community events which provide an opportunity for the community to come together and which help to cement the identity of the town and creates a sense of community. | Ongoing | Commenced | Continued support for Community events such as the All British Day.
9 | Advocate for a broader range of in-home and transport services to operate throughout the town so that the elderly and disabled can continue to remain within the Echunga community. | Ongoing | Commenced | Council provides services through HACC and has partnered with the RDA to adopt the Regional Public Transport Strategy aimed at increasing regional transport options.
10 | Provide information to the Echunga community on the housing support services available throughout the District, connecting those experiencing housing difficulties with the appropriate services. | Ongoing | Commenced | Council has developed a directory of housing support service providers that have a presence in the District. This information is made available on Council's website www.mountbarker.sa.gov.au/community/community-directory/support-for-the-vulnerable-and-homeless
11 | Continue to provide facilities which cater for informal recreation activities to engage younger residents and support community groups which perform this role. | Ongoing | Commenced | Council has recently supported the ECA to develop an informal mountain bike pump track at the Echunga Community Park. There is a need to also investigate increasing public access to recreation facilities at the recreation ground e.g. tennis courts/netball courts and a need to renew some facilities such basketball rings.
12 | Where possible support the role, function and growth of the Echunga Primary School to continue to provide desirable local education options for the town. | Ongoing | Commenced | Council Continues to advocate for quality local education facilities through the Regional Education Forum. Council also acknowledges that need to consider access and parking issues at the school and is willing to work with both the Primary School and Recreation Ground Committee to consider this as the school grows.
13 | Improve the quality of pedestrian and cycling links throughout the town, identifying locations for creating new infrastructure for more safe and efficient movement. | Medium | Commenced | Council is working through a program of constructing new footpaths throughout the town. Work already completed includes paths through the Echunga Community Park, new paths on the western side of Echunga Road and Strathalbyn Road. Council is currently working on the design for new footpaths on Churchill Road, the mains street and Strathalbyn Road at the eastern end of the town leading Sophia Street.
14 | Advocate for a DPTI led review and upgrade of Adelaide Road, Church Hill Road intersection to improve pedestrian and vehicular safety whilst accommodating an improved interface to the heritage listed Hagen Arms. | Long | Completed | DIT have done some line marking to improve the movement of vehicles through the intersection, providing the pub with increased safety more breathing space. Further to this, the design work for the main street project will consider the treatment for the roadside verges at this intersection.
15 | Improve wayfinding signage throughout the town to encourage greater visitation to the main street. | Short | Not Commenced
16 | Advocate for improved public transport services and associated infrastructure throughout the town. | Ongoing | Commenced | Council continues to advocate for improved public transport options across the District and has partnered with the RDA to adopt the Regional Public Transport Strategy aimed at increasing regional transport options.
17 | Undertake improvements to the school crossing to improve the safety and visibility the crossing and investigate the extension of the 60km/h speed limit the Dolman Road Echunga Road intersection. | Short | Completed | Council worked with the Department for Infrastructure and Transport to deliver an upgrade to the pedestrian crossing opposite the school. This is now a signalised crossing at school times.
18 | Investigate and review existing trail network within and around Echunga as to inform potential for improvements to increase usability. | Medium | Commenced | This work has commenced as part of Council's Open Space Strategy.
19 | Establish the RSL Garden of Remembrance land at the intersection of Echunga Road and Strathalbyn Road as a public reserve in order to encourage greater use and functionality (see concept plan). | Medium | Commenced | Council has supported the ECA to start development of the park. To date the land has been further developed with additional paths, tree planting, sensory garden, mountain bike track pump track, boundary fencing, picnic shelter, power to the site and a rain water tank. Council is now considering the most appropriate maintance levels for the new space. Further work is required to deliver on the concept plan identified in the Township Plan.
20 | Continue to support the Echunga Memorial Institute Committee to provide a range of community activities provided by local interest groups to encourage and support improved social inclusion outcomes for the community. | Ongoing | Commenced | The upcoming mainstreet design will consider how to support the use and function of the building for community uses.
21 | Continue to support the use of the Scout Hall land at the intersection of Echunga Road and Strathalbyn Road for use by a range of social and recreation groups. | Ongoing | Commenced | Council is supporting the Scout group to continue to use the land and some proposed improvements include a new front boundary fence.
22 | Support the community to manage and protect native vegetation conservation areas including Echunga Cemetery and Stringybark Reserve along Berry Road. | Ongoing | Not Commenced
23 | Work with the Primary School, church and community groups to identify opportunities to share their facilities for community use. | Ongoing | Commenced | With the development of the adjacent Community Park, the primary school can now make use of this space as an outdoor education area.
24 | Support the continued use of the Recreation Grounds by sporting and community groups to increase participation and social inclusion. | Ongoing | Commenced | Council supports local sporting teams through the provision of facilities and infrastructure working with the Recreation Ground management committee. A recent project has included the resurfacing and netball courts.
25 | Continue to support community events such as the All British Day to occur within the Recreation Ground. | Ongoing | Commenced | Continued support for Community events such as the All British Day, supporting local sporting teams through the provision of facilities and infrastructure through the Recreation Ground management committee.
26 | Support the Recreation Grounds Committee to secure funding to for improvements to existing netball courts, including widening and resurfacing the playing surface. | Short | Completed | Funding was secured to complete this project and the resurfacing of the courts has now been completed. The courts are open to the public.
27 | Support the Recreation Grounds Committee where possible to improve the visibility and appearance of entrance to the Recreation Grounds e.g. entrance statement and signage. | Short | Completed | Entrance statement to the recreation grounds is has now been constructed, improving the visibility to the entrance to the site.
28 | Seal the road surface around the northern end of the main oval to improve access. | Medium | Not Commenced
29 | Provide for overnight RV parking, including provision for and RV dump point at the rear of the existing football club rooms. | Medium | Commenced | Council is currently working on a program of establish RV parks at a number of smaller towns throughout the District. Establishing and RV park at Echunga will form part of this program in coming years.
30 | Extend the existing football club rooms to provide for women’s and umpire change rooms. | Medium | Not Commenced
31 | Resurface existing tennis courts to improve the playing surface and improve public accessibility. | Medium | Not Commenced
32 | Refurbish existing public toilets to provide for disabled facilities and access. | Medium | Not Commenced | Under investigation.
33 | Continue to support the Kidman Trail trail-head site at the southern end of the Recreation Grounds. | Ongoing | Not Commenced
34 | Install fitness stations around the oval to improve opportunity for informal exercise. | Short | Not Commenced | There may be the potential to funds this through Council's Community Grants Scheme.
35 | Develop and promote touring routes throughout the Adelaide Hills which connect visitors to Echunga. | Medium | Not Commenced
36 | Continue to support major community events which contribute to the local economy and support existing local businesses. | Ongoing | Commenced | Continued support for Community events such as the All British Day.
37 | Continue to provide support to local businesses by providing access to Council’s Economic Development Officer and linking the business community with education and professional development programs. | Ongoing | Commenced | Council's Economic Development Officer will engage with businesses owners and provide support where required.
38 | Investigate the effectiveness of the existing Local Centre Zone policies, and consider alternative policies that encourage a more broad range of commercial and residential development such as that within the Township Zone. | Medium | Completed | The State Government's Planning and Development Code has resolved this action with Zoning policies which consider a boarder and more diverse range of land uses.
39 | Undertake improvements to the main street, with landscaping treatments, street trees, lighting, street furniture and footpath surfaces being the key elements (see concept plan opposite). | Medium | Commenced | Council has commenced the first stage of this project, which includes preparing a concept design for the future upgrade of the street. This work is currently underway and should be completed and presented to the public for feedback by miss 2023. Following this a detailed design process will occur to prepare civil designs, engineering and staging plans for construction. Following this design process Council will be in a good position to apply for grant funding and budget for the construction of this project.
40 | Improve the efficiency of on-street parking at key activity points, with one example being to investigate the relocation of the existing bus stops to provide additional parking adjacent the Post Office and General Store. | Short | Commenced | The will be addressed as part of the design work for the main street, as per action #39.
41 | Advocate for a Power Line Environment Committee (PLEC) program to underground the overhead power lines on the southern side of the main street, allowing for an improved streetscape and street tree design. | Long | Commenced | The purpose of this action is to allow for a streetscape that can feature street trees on the southern side o the mains street. Council is considering the best approach to delivering this outcome including alternative options such as areal bundling and smart tree species selection.
42 | Undertake a review of existing storm-water management within the township in the medium term. | Medium | Not Commenced
43 | Educate property owners on best practice management of creek lines within private ownership. | Ongoing | Not Commenced