## Hahndorf
Action Number | Endorsed Action | Endorsed Timeframe | Status as of March 2025 | Comment | Column1
1 | Advocate and support the continued protection of heritage places and areas | Ongoing | Commenced | Established through PDI Act and State Heritage Area. | complete
2 | Celebrate heritage and culture of the area through iniatives such as interpretive signage, public art and the materials chosen for the public realm | Ongoing | Commenced | Ongoing through BAU. Improvements to Old School House budgetted to be undertaken in 22/23 financial year. | complete
3 | Work in partnership with SA heritage branch to continually inform and facilitate community and trader information sessions on planning and development of State Heritage Places | Ongoing | Ongoing | Working and constant dialogue with State Heritage regarding a number of projects. | complete
4 | Reinforce detached dwellings on large allotments, whilst investigating opportunities for housing diversity in appropriate locations (outside of heritage areas). | Ongoing | Commenced | As supported and integrated within the Planning and Design Code and relevant related planning controls. | complete
5 | Encourage private property owners to improve their land and buildings in line with heritage objectives that have an interface with important public spaces. Investigate the viability and costs of an incentive scheme to achieve this. | Ongoing | Commenced | Heritage incentive scheme available through application to Council. | complete
6 | Improve the appearance of township entrances and approaches. Develop gateway treatments that reflect the local sense of place and heritage. | Ongoing | Not Commenced | Project commencing as part of the State/Federal and Council funded project proposla which reamins subject to funding | in progress
7 | Implement short-term strategies to maximise use of existing car parking | Short (0-3 years) | Commenced | Council are active in implementing both short and long term actions to address car parking issues within Hahndorf. Further investigations and interventions will continue | in progress
8 | As a priority, begin investigations to develop strategies to alleviate car parking supply and demand issues in the Main Street. | Short (0-3 years) | Commenced | Council are active in implementing both short and long term actions to address car parking issues within Hahndorf. Further investigations and interventions will continue | in progress
9 | Extend the Pine Avenue footpath to Hahndorf Recreation Ground. | Short (0-3 years) | Completed | Completed. | complete
10 | Investigate opportunity to construct a pedestrian refuge at Beerenberg on Mount Barker Road. | Short (0-3 years) | Completed | Completed. | complete
11 | Seek opportunities to create a trail along the creek line from the Arts and Culture Precinct to Alec Johnston Park | Ongoing | Commenced | Work commenced on Academy upgrades. Council supporting the HCA to progress localised creek improvements. | in progress
12 | Investigate appropriate strategies to encourage cyclists. | Ongoing | Commenced | Council staff promoted this through the progression of the Main Street Detailed Design process with DIT. | complete
13 | Integrate cycling and walking trails to connect key destinations such as Women’s Pioneer Trail, the Cedars and Blueberry Hill Trail to the Main Street. | Medium (3+ years) | Commenced | Pioneer Womens Trail extension (3m wide shared path) now forms part of the scope of works for Main Street Improvements which remains subject to funding. Ambleside Road Concept currently being progressed by Council. | in progress
14 | Advocate for the construction of a 4 way interchange at Verdun. | Ongoing | Commenced | An active and funded DIT project that is proposed to commence in 2025/26. | in progress
15 | Undertake study at schools including: | Short (0-3 years) |  |  | future
16 | Redefine the priority of the Auricht Road / Auricht Close intersection. | Medium (3+ years) | Not Commenced |  | future
17 | Investigate removal of on-street parking directly adjacent the Balhannah Road / Mt Barker Road intersection to improve traffic flow. | Short (0-3 years) | Not Commenced | Improvements to the Balhannah Road and Mount Barker Road intersection inclusive fo parking considerations forming part of the Main Street Improvements Project which reamin subject to funding | in progress
18 | Improve sight lines at the Johns Lane / Auricht Rd intersection. | Medium (3+ years) | Not Commenced |  | future
19 | Advocate for improved public transport services and infrastructure, for example a park n’ ride, better shelters and paths. | Ongoing | Commenced | Ongoing through business as usual and in association with DIT. | in progress
20 | Investigate alternative routes for heavy vehicle traffic to bypass the main street. | Medium (3+ years) | Completed | Heavy vehicles (over 15m in length) are now redirected to River Road and not permitted within the main street. | complete
21 | Reinforce the Hahndorf Recreation Ground as a key destination for community sporting facilities. | Ongoing | Commenced | Ongoing. | in progress
22 | Enhance Alec Johnston Park through improved play space and creek corridor. | Medium (3+ years) | Commenced | Play space upgrade completed. Further creek improvements to be implemented in colloboration with the Hahndorf Community Association. | in progress
23 | Enhance the creek through Alec Johnston Park and pocket parks with an aim to educate people on ‘best practice’ creek maintenance and enhancement. | Short (0-3 years) | Commenced | Council support for community intervention (St Michaels Primary School and the HCA) | in progress
24 | Continue to develop the Bowling Club facility as an important community space and investigate possible options for surplus land within the Bowling Club grounds. | Short (0-3 years) | Commenced | Council supports the roel and fucntion of the Jhahndorf Bowloing Club and it remains as a relevant community faiclity Several improvements to the Bowling Club have been undertaken in recent years. | in progress
25 | Establish passive play, low key, minor trails in bushland areas at Yantaringa Reserve and Hahndorf Recreation Ground. | Ongoing | Commenced | Bike trails and landscape improvements undertaken at Yantaringa and Tara-Illa. No future stages programmed at this stage. | in progress
26 | Investigate opportunities for greater community use of the Hahndorf Recreation Ground, for example a youth space and/or outdoor gym equipment. | Ongoing | Commenced | Investigations complete | complete
27 | Support the community to manage and protect native vegetation areas including adjacent Hahndorf Recreation Ground, Yantaringa Reserve and other community re-vegetation projects. | Ongoing | Commenced | Council continues to support the management and protection of native vegetation in Yantaringa Reserve and at the Hahndorf Recreation Ground. | complete
28 | Work with the Hahndorf Institute Committee to increase shared community use of the building and grounds to ensure a high level of utilisation. | Ongoing | Commenced | Business as usual. | complete
29 | Work with the local schools, church and community groups to identify opportunities to share their facilities for community use. | Ongoing | Commenced | Business as usual. | complete
30 | Work with Hahndorf CFS to investigate potential relocation to a more convenient location. | Ongoing | Commenced | Initial comments sought from SAFECOM/CFS - no further work undertaken | complete
31 | Brand and promote Hahndorf alongside the Hahndorf Traders and Business Association (HTBA), South Australian Tourism Commission (SATC) and Adelaide Hills Tourism (AHT) for its heritage, landscape quality and environment, and tourist experiences. | Medium (3+ years) | Commenced | Ongoing through business as usual and primiarly promoted through the HBTA. | complete
32 | Encourage and foster the inclusion of Germanic experiences and East Prussian heritage, for example streetscape elements in the Main Street such as flower boxes. | Ongoing | Commenced | Main Street upgrade design completed and remains subject to funding and prioritisation | in progress
33 | Install free Wi-Fi along the Main Street. | Medium (3+ years) | Not Commenced | Main Street upgrade design completed and remains subject to funding and prioritisation | in progress
34 | Develop and promote touring routes through the Adelaide Hills which connects to other towns and experiences in the region with the aim to increase overnight stays. | Ongoing | Commenced | Economic Development team continue to work on promoting touring routes | complete
35 | Acknowledge the high visitation rates of international tourists to Hahndorf and investigate implementing multi-lingual signage (e.g. German, Chinese and English) on key way finding / interpretive points. | Short (0-3 years) | Not Commenced | inclusoive witihn Main Street upgrade design and remains subject to funding and prioritisation | in progress
36 | Incorporate smart cities technology to gather and share data to inform decision making (e.g. car parking sensors). | Short (0-3 years) | Not Commenced | inclusoive witihn Main Street upgrade design and remains subject to funding and prioritisation | in progress
37 | Renew footpaths on both sides of the Main Street (to the kerb) and include interpretation as well as safety elements. | Short (0-3 years) | Commenced | Main Street upgrade design completed and remains subject to funding and prioritisation | in progress
38 | Upgrade street furniture (for example seating and bins) along the Main Street which enhances the sense of place and identity. | Short (0-3 years) | Commenced | Main Street upgrade design completed and remains subject to funding and prioritisation | in progress
39 | Upgrade street lighting / install feature lighting along the main street and extend lighting to Carl Nitschke Memorial car park to enhance safety and street activation. | Ongoing | Commenced | Main Street upgrade design completed and remains subject to funding and prioritisation | in progress
40 | Undertake and implement a succession plan of all street trees along the Main Street. | Short (0-3 years) | Commenced | Work commenced on succession planning - new trees planted in Main Street. | complete
41 | Renew signage and way finding, and reduce unnecessary visual clutter in the public realm. | Ongoing | Commenced | Council has implemented improved signage and marketing material to improve accessibility. | complete
42 | Develop The Academy as a key cultural and arts precinct and integrate Wolf Blass Museum, the Old School House and The Academy - see following page for concept. | Ongoing | Commenced | . Council continue to support the function of the Hahdorf Academy | in progress
43 | Activation of the public realm through art, music and performance to enhance the customer experience. | Ongoing | Not Commenced | Public Realm improvements integrated witin the main street designw hich remains subject to funding and prioristations | in progress
44 | Support programming of events in evenings to support an expanded evening economy. | Short (0-3 years) | Commenced | Council continue to work on programming of events in partnership with HBTA and other key stakeholders. | complete
45 | Continue to support and work with Hahndorf Business and Tourism Association. | Ongoing | Commenced | Council continue to support and work with HBTA | complete
46 | Prepare a Stormwater Management Plan (SMP) in accordance with the Stormwater Management Guidelines. A SMP will provide: (a) Catchment specific objectives for management of stormwater runoff from the catchment. (b) Potential management strategies that could be used to meet the identified management objectives. (c) Estimated costs and benefits associated with each type of strategy. (d) Clear priorities, responsibilities and time frames. | Ongoing | Commenced | SWMP partially completed. DIT currently completing asset assessment in context of Main Street Improvements. | in progress
47 | Liaise with Natural Resource Management to improve land management practices and continually inform and facilitate public information sessions on how to manage creek lines. | Ongoing | Not Commenced | Not commenced. Council to progress district-wide. | future