## Harrogate and Brukunga
Action Number | Endorsed Action | Endorsed Timeframe | Status as of March 2025 | Comment
1 | Continue to support the ongoing recovery and resilience efforts of the communities of Harrogate and Brukunga wherever possible. | Ongoing | Commenced | Ongoing community support provided by a range of Council services.
2 | Review roadside vegetation management and determine additional maintenance that may be required. Where necessary implement improved maintenance program in identified issue areas as a priority. | Bushfire Response | Commenced | As part of programmed works across the District, Council's Maintenance and Operations (MOPS) team monitors and maintains roadside vegetation where necessary.
3 | Review supply/access for fire fighting water with the CFS and assist with the implementation of additional dedicated water tanks and improved access for fire fighting purposes at Harrogate and Brukunga. | Bushfire Response | Commenced | Council continue to work with the CFS regarding improved supply and access to water for fire fighting purposes.
4 | Council to review the condition of the unsealed section of Harrogate Road south of Harrogate, prepare design and upgrade while considering opportunity for combining such a project with improved pedestrian infrastructure. | Bushfire Response | Completed | Harrogate Road now sealed.
5 | Council to liaise with telecommunication service providers and advocate for improved service provision. | Bushfire Response | Completed | Digital connectivity plans prepared for the district by Telstra and NBN Co. and endorsed by Council in November 2024. Currently in discussions for application for grant funding and improved services.
6 | Council to proactively communicate and where necessary educate property owners district wide of best practice fire prevention measures and promote early implementation of individual bushfire survival plans in emergency situations. | Bushfire Response | Ongoing | On an annual basis Council proactively engages with community regarding fire preparedness and response. The formation of Council's Fire to Flourish team assisted to prepare community regarding the development of bushfire prevention plans and associated projects across the district.
7 | Review the condition of existing native vegetation areas and implement sensitive bush care and/or revegetation planting where appropriate. | Bushfire Response | Commenced | Ongoing. Revegetation programs initiated and promoted by Council.
8 | Weed management of the Bremer River within Harrogate and Dawesley Creek within Brukunga should be undertaken. | Bushfire Response | Commenced | Weed management within the Bremer River forms part of ongoing maintenance programs of waterways across the district.
9 | Advocate and support the continued protection of heritage places. | Ongoing | Completed | Council successfully promoted the protection of heritage places which are now embedded within the South Australian Planning and Design Code.
10 | Celebrate indigenous and european heritage and culture of the area through initiatives such as interpretive signage, public art installations and the materials chosen for public realm improvements. | Ongoing | Commenced | Council are finalising the installation of public art in Brukunga which references First Nations culture.
11 | Reinforce existing township boundaries and promote opportunities for improved entry statements for each township. | Short | Completed | Township boundaries consistent with that of Council's previous Development Plan have been successfully embedded with the South Australian Planning and Design Code.
12 | Assist the community to action small scale streetscape improvements within the public realm within Harrogate and Brukunga. | Ongoing | Commenced | Plans are being considered within both Harrogate and Brukunga to improve areas of open space where possible.
13 | Advocate for an installation for public art in reference to and in acknowledgement of indigenous Peramangk history in Brukunga. | Short - Medium | Commenced | Council are finalising the installation of public art in Brukunga which references Aboriginal culture.
14 | Continue to support the role and function of community and sporting groups, acknowledging the important role they play to encourage social interaction and inclusion. | Ongoing | Commenced | Business as usual through a range of Council departments.
15 | Continue to support local community events which provide an opportunity for the community to come together and which helps to cement the identity of the town and creates a sense of community. | Ongoing | Commenced | Business as usual through a range of Council departments.
16 | Encourage improved use of Council’s Hills Community Transport program and advocate for improved public transport services. | Ongoing | Action transferred | Staff investigating options with Keoride for an extension beyond the current zone map. The ITP now leads this initiative.
17 | Continue to provide facilities which cater for informal recreation activities to engage younger residents and support community groups which perform this role. | Ongoing | Commenced | Plans are being considered within both Harrogate and Brukunga to improve areas of open space where possible.
18 | Council to undertake a condition review of existing roads in Harrogate and Brukunga and implement any required maintenance of identified roads and if necessary road upgrades to improve access and egress to the towns. Priority for the upgrade of the unsealed section of Harrogate Road and consideration of Military Road, Wachtel Road and Laurie Road. | Short | Commenced | Post bushfire, the local road network was investigated and roads where immediate works required were prioritised.
19 | Council to review existing pedestrian provisions and undertake a needs analysis to consider where improvements are needed and implement where required with priority to improving safe and ease of movement between key destinations. | Medium | Commenced | Footpath audit undertaken and the Council wide Footpath Program initiated.
20 | Implement improved pedestrian focused safety signage on entrances to townships. | Short | Commenced | Kangaroo warning signs installed to the south of Brukunga township along Pyrites Road following community concern. Council remains open to further investigations and responses should a concern be raised.
21 | Review existing condition of access driveway and culvert over the Bremer River to the Harrogate Reserve and undertake improvement works if and when required. | Medium | Commenced | Existing condition reviewed but no works undertaken.
22 | Council to review existing community facilities, open space and trail network in the short term as to inform any identified potential improvements required. | Short | Commenced | Plans are being considered within both Harrogate and Brukunga to improve areas of open space where possible. To note, the upgrade of the Brukunga court has been completed (December 2024).
23 | Following the review, undertake improvements to existing community facilities, open space and trails consistent with identified needs/priorities across the townships and broader district noting that all projects would be subject to future funding allocation. | Ongoing | Commenced | Plans are being considered within both Harrogate and Brukunga to improve areas of open space where possible. Future open space improvements will be subject to budget commitment and prioritisation.
24 | Improve community useability of James Hammer Memorial Reserve, Brukunga such as consideration of passive play elements, unsealed footpath and landscaping. | Medium | Commenced | Plans are being considered within both Harrogate and Brukunga to improve areas of open space where possible.
25 | Improve the appearance of township entrances and approaches. | Medium | Action transferred | To be undertaken in future stages of the Township Plan Entry Statements Program.
26 | Improve basic wayfinding signage within townships to open space areas and key destinations. | Short | Not Commenced
27 | Provide public seating and activation node nearby the Harrogate Memorial Hall and provide improved formalisation of car parking on Council land. | Medium | Commenced | The Harrogate Soldiers Memorial Hall were successful in obtaining a grant to implement these works.
28 | Formalise walking trail loop from Laurie Road to the Harrogate Cemetery. | Short - Medium | Completed | Trail constructed and being utilised by community.
29 | Investigate potential for formalised access to land west of Smilie Street, Brukunga for improved community use and access purposes. | Short | Completed | Initial investigations undertaken with the Department for Energy and Mining (DEM). Access is not possible on this land and this action has been completed.
30 | Educate and inform local residents on appropriate roadside management practices and native vegetation protection. Investigate suitable mechanism for this to occur. | Short | Commenced | Undertaken through Council's Maintenance and Operations (MOPS) team.
31 | Advocate, support and partner with existing groups such as Trees for Life for bush care or revegetation projects within Harrogate and Brukunga and surrounds. | Short - Medium | Commenced | Commenced through Council's Environmental Assets team.
32 | Undertake sensitive bush care and revegetation planting on Council land where possible and support volunteers. | Ongoing | Commenced | Ongoing. Revegetation programs initiated and promoted by Council.
33 | Advocate and promote the building of Climate Resilient homes within the district as informed by the Where We Build What We Build project recommendations. | Ongoing | Commenced | Relevant staff continue to advocate for climate resilient housing solutions to external organisations. Specifically the Homes for Tomorrow project assists to address this action.
34 | Undertake a review of existing stormwater management within the townships. | Short - Medium | Commenced | Watts Road and Pyrites Road drains renewal undertaken. Council has reviewed stormwater drainage within Brukunga following community interest.
35 | Undertake a review of existing kerb and pedestrian footpaths within the township as to inform potential for infrastructure upgrades in the context of already programmed and future proposed works. | Short | Completed | Footpath audit undertaken and the Council wide Footpath Program initiated.
36 | Continue working with the CFS to ensure Bushfire Management Plans are up-to-date. | Ongoing | Commenced | Ongoing through a number of Council departments.
37 | Advocate for an extension of SA Water infrastructure to service Harrogate. | Ongoing | Completed | Initial investigations undertaken with SA Water and no further action will be undertaken.