## Kanmantoo
Action Number | Endorsed Action | Endorsed Timeframe | Status as of March 2025 | Comment
1 | Ensure ongoing protection and enhancement of heritage places. | Ongoing | Ongoing | Ongoing through Council business as usual. Notably, consistent messaging from Development Assessment and Strategy Planning teams to the community, developers and State government.
2 | Celebrate the heritage and culture of the area through initiatives such as interpretive signage, public art installations and the materials chosen for public realm improvements. This should look to highlight events and/ or people of significance (including but not limited to the mining history of the town and the town's connection to David Unaipon) and include, when appropriate, collaboration with traditional owners in such acknowledgements and installations. | High | Not commenced
3 | Ensure future residential development occurs within the existing town boundary. | Ongoing | Ongoing | Business as usual through enforcement of zoning controls as per the Planning and Design Code/ PDI Act.
4 | Continue the implementation of Council's Community Development Lead Strategy so that groups such as K4C and the Grounds Committee are supported through a range of resources such as training and volunteering oppportunities. | Ongoing | Ongoing | See Council's Community Development Lead Strategy.
5 | Support the community in establishing and maintaining a residents' association should there be a push for the creation of such a group, to assist in coordination of works and activities through the town. | Ongoing | Ongoing | There has been no push from the community on this action. Council remains open should this become more desirable in the future as the community evolves.
6 | Continue to operate the Hills Community Transport (HCT) service, ensuring demand is monitored and service is adapted as needed. | Ongoing | Ongoing | Ongoing through Council business as usual.
7 | Advocate for improved public transport services and associated infrastructure for the township. | Ongoing | Ongoing | To be taken up by the Public Transport Action Plan under Council's Integrated Transport Plan (ITP). Ongoing through interaction with the Department for Infrastructure and Transport (DIT).
8 | In line with Council's footpath program, complete sealed footpath connection from the northern end to the southern end of the town, linking the existing path along the Main Street to the property at 47 Mine Road (Lot 134), including improvements to the Mine Road/ Cook Street bus stop. | Low | Commenced | Proposed for design in 2027/28 and potential delivery in 2028/29 within Assets' New Footpath Program.
9 | Review access and connections as part of Council's new footpath strategy to provide all weather access along the extent of Kent Road, Atkinson Road and Young Road. | Low | Not commenced | Not currently considered a priority.
10 | Investigate a cycling and walking trail between Kanmantoo and Callington away from the Old Princes Highway. | Low | Not commenced | This is not presently considered feasible but the logic and community desire are noted. Trails to be addressed in Council's Open Space Strategy.
11 | Investigate opportunities to minimise the impacts from truck movements from nearby industrial land uses (e.g. Hanson, Hillgrove and Neutrog) through proper and open responses to complaints received in relation to trucks travelling through the town and in use of private roads that act to bypass the township. | Low | Commenced | Planning Strategy to work together with Infrastructure, City Development and the community as required.
12 | Through Council's existing 'Open Space and Trails Review and Update' (2023/24), ensure that Hutton Reserve is maintained as the town's primary reserve and consider additional open space/ trail facilities/ upgrades. | Ongoing | Ongoing | To be addressed in Council's Open Space Strategy.
13 | Improve useage of the community bike track facility through possible alternate designs or land uses, such as a nature reserve, off-leash dog park, private use or other. | Medium | Not commenced | May be examined in Council's Open Space Strategy.
14 | Work with the Kanmantoo Hall Committee to understand their long term needs with regard to access to the Town Hall and surrounding space for Anzac day and other occasions of community significance and in promoting the broader use of the Town Hall and surrounds through physical improvements such as toileting facilities, lighting, access, signage or other works. | Medium | Not commenced
15 | Partner with K4C to develop mining related tourism, taking advantage of equipment that Hillgrove Resources have such as walking trails, rehabilitation sites, historic buildings/ sites and/ or lookouts. | Ongoing | Ongoing | Economic Development Officer open to contacting K4C and furthering discussions on tourism related works with Planning Strategy.
16 | Work with new and established local businesses to improve opportunities and knowledge of grants and resources by linking them in with Council's Economic Development team for tailored advice. | Ongoing | Ongoing | Economic Development Officer has held discussions with local businesses on economic development. Further workshops or the like can be arranged as desired.
17 | Seek opportunities with prospective customers on the sale of recycled water on a commercial basis, achieving environmental, economic and social benefits to the community. | Ongoing | Ongoing | Wastewater Business Development to remain open on this. Discussions have been had with Hanson on the sale of recycled water.
18 | Improve the appearance of township entrances and approaches. Develop gateway treatments that reflect the local sense of place and act to calm traffic through the Main Street. | High | Not commenced | To be undertaken in future stages of the Township Plan Entry Statements Program.
19 | Support opportunities to increase activation and community use to the Main Street whether through private or commercial use, making sure to not detract from local heritage. | Medium | Not commenced | Planning Strategy to remain cognisant of this and hold disussions with Economic Development or City Development as needed.
20 | Informal recreation trail parallel to the Main Street, with landscaping treatments, street trees, lighting, street furniture and footpath surfaces being the key elements as per the concept plan. | Low | Not commenced
21 | Provide support for any community groups and/ or volunteers wishing to undertake environmental initiatives on public land such as re-vegetation, weeding and stabilisation/ erosion management on degraded landscapes in particular along the creek line. | Ongoing | Ongoing | Ongoing through Council's Environment and Natural Assets team.
22 | Revisit tree plantings along Mine Road to ensure appropriateness to the climate, giving consideration to aesthetics and management. | Low | Not commenced
23 | Continue to work with Hillgrove Resources, Hanson and Neutrog to deliver environmental and amenity outcomes, and specifically as relate to interface issues such as dust suppression, odour, noise and vibration. | Ongoing | Commenced | Strategy Planning and Development Assessment/ City Development to communicate community concerns and enforce requirements of DNF's as required.
24 | Undertake a review and update to flood mapping plans and flood plain extents for the Kanmantoo and Callington townships. | High | Not commenced | Infrastructure and Assets aware of this shortcoming. Not commenced as yet.
25 | Work with the LGA CWMS Management Committee to determine the priority of connection of Kanmantoo to a Community Wastewater Management System (CWMS). | Low | Commenced | Wastewater Business Development to continue to periodically query this. Kanmantoo's connection to CWMS not currently a priority.
26 | Council to advocate for improved telecommunications services. | Ongoing | Ongoing | Digital connectivity plans prepared for the district by Telstra and NBN Co. and endorsed by Council in November 20240. Currently in discussions for application for grant funding and improved services.