## Littlehampton
Action Number | Endorsed Action | Endorsed Timeframe | Status as of March 2025 | Comment
1.1 | Develop an attractive and well designed public realm along North Tce/Old Princes Hwy, including staged undergrounding of power lines between Cleggett Rd and Darnley St. | Short (0-3 years) | Completed | Complete
1.2 | Provide a continuous and safe footpath along North Tce/Old Princes Hwy that links Adelaide Rd, Mount Barker, to Anembo Park, Littlehampton’s village centre and on to the Glebe land. | Short (0-3 years) | Commenced | Littlehampton to Anembo Connection Design being undertaken.
1.3 | Construct (and renew) footpaths and crossings in residential neighbourhoods to develop safe walking routes that connect residents to destinations such as shops, the Primary School and open space. | Ongoing | Commenced | District wide audit undertaken and footpath priorities to be undertaken within the Footpath Program.
1.4 | Prioritise footpath construction to complete highly used routes, fill in strategic gaps and provide good links to Blakiston, Totness and Mount Barker. This could include West Tce, Junction Rd, Kym Ave, Gardner St, Baker St, Williams St and Darnley St. | Medium (3+ years) | Commenced | District wide audit undertaken and footpath priorities to be undertaken within the Footpath Program.
1.5 | Take advantage of the linear parks and laneways in the northern part of Littlehampton to create a walking/cycling loop that includes the reserves at Benjamin Gray Drive, Andrewville Tce, Kym avenue, Lloyd Cres and the Spring Park Farm Reserve. | Long | Not Commenced
1.6 | Identify the route for, and complete the trail extension from Mount Barker into Littlehampton. | Medium (3+ years) | Completed | Childs Road footpath completed.
1.7 | Develop a shared trail along the railway corridor from Anembo Park, crossing Junction Rd and joining the walking cycling loop proposed for the Spring Park Farm area. | Medium (3+ years) | Not Commenced
1.8 | Ensure developers provide adequate standard of footpaths in new residential developments. | Ongoing | Commenced | Ongoing
1.9 | Implement innovative approaches to path construction that enable more paths to be built at lower cost. | Ongoing | Commenced | Ongoing Council wide initiative and considered within the Footpath Program.
2.1 | Work with DIT to provide more pedestrian crossings on North Tce and Junction Rd. | Ongoing | Commenced | Complete, refer Action 1.1
2.2 | Review speed limits with DIT with an aim to slow traffic at key points and increase road safety, including for pedestrians and cyclists, on Junction Rd (between Benjamin Gray Dr and Kym Ave) and Old Princes Hwy (between Gardner St and Fulford Tce). | Medium (3+ years) | Completed | 7/7/2020: Work commencing with DPTI to look at 50km speed limit.
2.3 | Improve signage at crossings, including the crossings in the commercial area and carparks around Foodland. | Medium (3+ years) | Completed
2.4 | Advocate for improved public transport services and infrastructure, including more regular bus services outside of commuter hours, better paths and shelters at bus stops, and a new bus stop at Anembo Park. | Ongoing | Commenced | Ongoing Council wide initiative.
2.5 | Promote new and existing trails to encourage more use of them. | Ongoing | Commenced | Ongoing Council wide initiative.
2.6 | In partnership with Littlehampton Primary School and community groups, facilitate more walking and cycling to school and support community events that promote the use of the trail and footpath network. | Ongoing | Commenced | Ongoing through Council business as usual.
3.1 | Renew and beautify the main street environment along North Tce/Old Princes Hwy (proposed landscape plan) including priority areas for power line undergrounding between Darnley St and Cleggett Rd. | Medium (3+ years) | Completed | Littlehampton Greening Project complete.
3.1 | Encourage private property owners to improve their land and buildings that have an interface with important public spaces. Investigate the viability and costs of an incentive scheme to achieve this. | Medium (3+ years) | Commenced | Council's Heritage Incentive Scheme provides for this initiative.
3.11 | Investigate renaming the main street of Littlehampton to achieve one consistent name through the town where there are currently four names. | Long | Completed | Investigated and not supported by DIT. Action complete.
3.2 | Define the ‘village centre’ with landscape treatments which ‘green up’ the public realm with more trees, replace bitumen with paving and plants, introduce water sensitive urban design features and more street furniture | Short (0-3 years) | Completed | Littlehampton Greening Project complete.
3.3 | Celebrate the heritage and culture of the area through initiatives such as interpretive signage, public art, and the materials chosen for public realm improvements. | Ongoing | Completed | Littlehampton Greening Project complete.
3.4 | Improve the appearance at township entrances and approaches. Develop gateway treatments that reflect the local sense of place. (see page 29 for one example of how this could be achieved at the Western town entrance near Anembo Park). | Medium (3+ years) | Commenced | Eastern approach complete and Littlehampton Greening Project complete
3.5 | Improve landscaping between Freeway and the entrance to Littlehampton, and around Anembo Park, with more plantings and clear pedestrian routes. | Medium (3+ years) | Commenced | Ongoing through Council business as usual.
3.6 | Progressively renew signage and wayfinding, and reduce unnecessary visual clutter in the public realm. | Ongoing | Commenced | Ongoing through Council business as usual.
3.7 | In partnership with community groups, strengthen existing measures that protect and enhance natural areas and Commenced manage bushland reserves. | Ongoing | Commenced | Ongoing through Council business as usual.
3.8 | Undertake watercourse restoration works with priority to Littlehampton Creek. | Medium (3+ years) | Completed | Ongoing. Revegetation, weeding and restoration works undertaken through business as usual.
3.9 | Undertake review of current maintenance levels of public places and reserves. | Medium (3+ years) | Commenced | Council currently reviewing maintenance service levels district-wide.
4.1 | Reinforce the desired character of existing residential neighbourhoods, whilst working to improve the character and aesthetics of entrances and the main street | Ongoing | Completed | Successfully integrated within the Planning and Design Code.
4.2 | Continue to limit urban development outside of existing zone boundaries. | Ongoing | Completed | Covered by EFPA within the Planning and Design Code.
4.3 | Review planning provisions to implement the directions of this Plan, and to update the Mount Barker Development Plan. The existing development potential of land currently zoned for urban or rural living uses is not to be reduced, but there may be opportunities for policy changes that lead to better outcomes of development. | Short (0-3 years) | Commenced | Integrated within the Planning and Design Code with further opportunities to be investigated.
4.4 | Encourage housing diversity and choice in appropriate locations including near major open space and activity centres. For example housing for older people, supported housing for people with disabilities and some medium density housing. | Short (0-3 years) | Commenced | As per action 4.3.
4.5 | Provide opportunity for businesses and local services through flexible and modern planning policy and infrastructure upgrades. | Short (0-3 years) | Commenced | As per action 4.3.
5 | Continue to upgrade infrastructure and services to appropriate standard for forecast population growth and urban development | Ongoing | Commenced | Completed and ongoing through the Asset Renewal Program and/ or specific projects.
5.1 | Implement staged wastewater and stormwater infrastructure upgrades | Short to medium | Commenced | WWTP to Hampden Rd New Gravity Sewer Trunk Main - Littlehampton Stage 10, plus stormwater works.
5.2 | Investigate the potential for an education facility at the Glebe that services the Nairne area as well as Littlehampton/Blakiston e.g. a school with secondary education offering. | Long | Completed | Not supported by Department of Education.
5.3 | Investigate the provision of charging stations for electric vehicles | Long | Not Commenced | Not commenced. Not currently a priority and aware of potential for this to be taken up by the private sector (as seen in Mount Barker Homemaker Centre).
5.4 | Progressively improve junctions, roads and car parks to enhance safety and performance, including for pedestrians and cyclists: | Ongoing | Commenced | Completed and ongoing through Asset Renewal Program and/or specific projects.
6 | Continue to develop and update existing public facilities and reserves, building on historic investment and recognising the value of these places to the community: | Ongoing | Commenced | Completed and ongoing through Asset Renewal Program and/or specific projects.
6.1 | Develop a detailed design for renewing Miels Park and the Peace Memorial Hall precinct as the ‘civic heart’ of Littlehampton. | Short (0-3 years) | Completed | Littlehampton Greening Project complete.
6.2 | Investigate provision of a car park behind the Hall on the old tennis courts, enabling the front of the park to be redeveloped and landscaped. | Short (0-3 years) | Completed | As per action 6.1
6.3 | Develop a program of works in consultation with the management Committee for the Hall to progressively update the Peace Memorial Hall in order for it to continue to be relevant as the main community venue in Littlehampton well into the future. Commence this work in time to celebrate the 100th birthday of the facility. | Short (0-3 years) | Commenced | The Hall, as a valuable community asset, continues to benefit from Council led improvements and renewals.
6.4 | Investigate the opportunity for a new community space to be developed by replacing the unsafe lean to structure at the rear of the Hall. | Short (0-3 years) | Commenced | Current project (March 2025). 7/7/2020: new netball storage area budgeted, community space within hall.
6.5 | Continue to develop Anembo Park as an important regional facility for sport and community activities. Add more passive recreation facilities (e.g. picnic seating and shelters, walking paths, water fountain), complete planned sports facility projects. | Ongoing | Commenced | Ongoing through business as usual. Various projects inc. Bike Track $40k, Hockey Pitch $1m, Tennis Club $60K, Road Sealing.
6.6 | Investigate extending the Anembo Park Clubrooms to provide additional flexible community space. | Long | Completed | 7/7/2020: not a current priority - look at filling the hall first before building new facility.
6.7 | Enhance existing local parks & natural areas to increase their use and amenity. This will involve low cost improvements | Ongoing | Commenced
7.2 | Work with community partners to add value to the St James School House so that the community can use and enjoy the historic structure and its setting more regularly. Undertake this in a way that complements the simple historic structure. | Ongoing | Commenced | Council continue to work with Blakiston Rotary regarding activation of this space.
7.3 | Investigate the viability and level of support for a dog park in Littlehampton. Investigate the northern portion of Fulford Tce Reserve as a possible location for this. | Medium (3+ years) | Commenced | In part completed through the safety improvements associated with the Littlehampton Greening project. 7/7/2020: considered at The Glebe.
7.4 | Provide features in all park and public space upgrades that support accessibility and social inclusion, and address identified community concerns. These include a desire for more play and activity opportunities for older children and teens, and aged friendly design. | Ongoing | Commenced | Littlehampton Greening project completed with further opportunities being investigated. 7/7/2020: considered in Glebe and Miels Park concepts.
7.5 | Apply the principles of ‘place making’ - providing more activities in public facilities and parks, incorporating public and community art, and work with community partners to make great places in Littlehampton. | Ongoing | Commenced
8.1 | Provide opportunities for residents to identify and lead community driven projects, within a Council provided framework that guides and encourages their initiative. | Ongoing | Commenced | Ongoing through Council business as usual. 7/7/2020: Commenced through Glebe and Miels Park concepts.
8.2 | Provide targeted opportunities for young people to contribute to the design and priorities for open space projects. | Ongoing | Commenced | Ongoing through Council business as usual.
8.3 | Establish a monitoring process (e.g. reference group) to track progress on this Plan with interested members of community and stakeholder groups. | Long | Commenced | This process is reliant upon existing staff resources in consultation with key community stakeholders. Ongoing and a dynamic process.
5.4.1 | Improve the intersection at Cleggett Rd and North Tce, focusing on pedestrian safety. | Medium (3+ years) | Completed | Complete. 7/7/2020: work complete.
5.4.2 | Improve the intersections of Gardner St and Gum Tree Dr with Old Princes Hwy to a standard suitable for anticipated traffic volumes. This will be required when further development occurs on Gardner St. | Medium (3+ years) | Completed | Completed and ongoing through the Asset Renewal Program and/ or specific projects.
5.4.3 | Continue to review sightlines, safety, function and design standard of roads where appropriate, with consideration of Alston Rd, Joseph Rd, Baker St, Blakiston Rd, Hallet Rd, West Tce, Rule Court, Kym Ave, Junction Rd, Childs Rd, Fulford Tce and the internal road at Anembo Park. | Ongoing | Commenced | Completed and ongoing through the Asset Renewal Program and/ or specific projects.
5.4.4 | Investigate opportunities to increase car park provision to support business activities, while also improving safety for pedestrians in car parking areas. | Long | Commenced | Completed and ongoing through the Asset Renewal Program and/ or specific projects.
5.4.5 | Investigate the viability of relocating car park from the front of Miels park to behind the Peace Memorial Hall | Short (0-3 years) | Completed | As per action 6.1.
5.4.6 | Wherever possible locate car parking behind or at the side of buildings along the main street to encourage active uses of buildings fronting roads and improve safety and quality of the public realm. | Ongoing | Commenced | Ongoing through Council business as usual.
6.7.1 | An all weather walking path at Coppin’s and Turner’s Bush reserves. | Long | Not Commenced | Not commenced. Not currently a priority.
6.7.2 | An ‘outdoor classroom’ at Coppin’s Bush e.g. seating logs | Long | Not Commenced | Not commenced. Not currently a priority.
6.7.3 | Picnic facilities and simple play elements in the Mitchell Court Reserve and the Spring Park Farm Reserve (e.g. at corner of Gum Tree Dr and Edson Cres) | Long | Not Commenced | Not commenced. Not currently a priority.