## Macclesfield
Action Number | Endorsed Action | Endorsed Timeframe | Status as of March 2025 | Comment
1 | Recognise the identity of the Macclesfield Township by acknowledging and supporting both social and recreational activities which support the creation of a cohesive and inclusive local community. | Ongoing | Commenced | Council currently supports local community, arts and sporting groups in the town.
2 | Further promote artistic and creative activities within the town, establishing Macclesfield as a centre for regional arts and culture and improve signage and wayfinding ending to support local artists. | Short | Not Commenced | Relevant staff of Council Council actively promote Macclesfield consistent with this action. No additional signage has been installed to specifically promote these activities.
3 | Continue to recognise the green and environmentally conscious culture within Macclesfield and support environmentally sustainable initiatives where appropriate. | Ongoing | Commenced | Commenced through business as usual.
4 | Promote Macclesfield as a key destination along existing tourist, cycling and scenic routes, encouraging greater numbers of visitors to the town. | Ongoing | Commenced | Commenced through business as usual.
5 | Continue to support local events which help to establish and promote the identity and character of Macclesfield. | Ongoing | Commenced | Council continues to support local community events.
6 | Support the creation and implementation of both Council and industry-led strategies to better recognise and support the many local businesses and rural enterprises which help to define the Macclesfield led township and its rural surrounds. | Medium | Commenced | Council have an Economic Development Officer. One of the functions of this role is to engage with business owners and provide support where required.
7 | Implement strategies to improve the arrival into the town, provide better-quality wayfinding throughout the town and entrance statements to encourage increased visitation to the main street and a greater understanding of the historic and cultural features of the town. | Medium | Not Commenced | To be undertaken in future stages of the Township Plan Entry Statements Program.
8 | Celebrate the heritage and culture of the town and its rural surrounds through initiatives such as interpretive signage, identification of important plantings and vegetation areas and public art displays, using multimedia platforms where possible. | Medium | Not Commenced
9 | Support the continued development of an interpretive walking trail which showcases Macclesfield’s Indigenous and European heritage | Medium | Not Commenced
10 | Continue to support the role and function of community and sporting groups, acknowledging the important role they play to encourage social interaction and inclusion. | Ongoing | Commenced | Council supports local sporting teams through the provision of facilities and infrastructure working with the Recreation Ground management committee.
11 | Continue to support local community events which provide an opportunity for the community to come together and which helps to cement the identity of the town and creates a sense of community. | Ongoing | Commenced | Council continues to support local community events.
12 | Advocate for a broader range of in-home services to operate throughout the town so that the elderly and disabled can continue to remain within the Macclesfield led community. | Short | Commenced | Commenced through business as usual.
13 | Continue to provide transportation services for the elderly and disabled through Council’s Hills Community Transport program and advocate for improved public transport services. | Ongoing | Commenced | Commenced through business as usual.
14 | Investigate changes to development plan policy which provide for smaller housing options throughout the town and which provides for aged and support care housing where appropriate to ensure that housing better caters for all of the town’s residents. | Short | Not Commenced | Enquiries received about this and DU zone changes. Not a priority to progress by Council but supportive of privately funded Code amendments that look to such amendments.
15 | Provide information to the Macclesfield community on the housing support services available throughout the district, connecting those experiencing housing difficulties with the appropriate services. | Short | Not Commenced | Council has developed a directory of housing support service providers that have a presence in the District. This information is made available on Council's website: www.mountbarker.sa.gov.au/community/community-directory/support-for-the-vulnerable-and-homeless.
16 | Continue to provide facilities which cater for informal recreation activities to engage younger residents and support community groups which perform this role. | Ongoing | Not Commenced | The best example of this is the skate facility a Davenport Square, however some more facilities such informal basketball area will be considered. The tennis courts are open to the public.
17 | Where possible support the role and function of the Macclesfield Primary School to continue to provide local education options for the town. | Ongoing | Commenced | Council has constructed a new footpath to the school along Vernon Street.
18 | Assist the community to develop and promote a community lead emergency and bushfire action plan. | Short | Commenced | Council's Fire to Flourish team have worked with representatives of the Macclesfield community to develop an emergency action plan.
19 | Improve the quality of pedestrian links throughout the town, identifying both Primary and Secondary pedestrian routes which require either new or more safe and efficient footpaths ensuring compliance with disability standards. | Medium | Commenced | Footpath to School recently upgrade, eastern side of mainstreet now has footpath along its entire length. To be further reviewed as part of the Council's existing Footpath Program.
20 | Promote the existing tourist routes which bring passing traffic and visitors to the town, supporting activities which improve the tourism experience in the town, including tourist accommodation. | Ongoing | Not Commenced
21 | Advocate for DIT-led improvements to the safety and condition of the rural road network around the town. | Medium | Not Commenced
22 | Improve signage and identification throughout the town, better linking visitors with key destinations, heritage and cultural sites and local businesses. | Short | Not Commenced
23 | Advocate for improved public transport services and associated infrastructure throughout the town. | Short | Not Commenced
24 | Continue to implement the intent of the Venables Street Master Plan to improve pedestrian access along the length main street including south of Sturt Street. | Medium | Completed | Mainstreet upgrade now completed on both sides of the street. Council now considers the Venables Street Master Plan now fully implemented.
25 | Investigate the potential to better manage vehicle parking in front of the Primary School with resurfacing and line-marking two potential solutions. | Short | Completed | Council has now installed wheel stops and created 90 degree parking and drop off area in front of the school.
26 | Provide greater clarity with regard to the use and management of the Lord Robinson Park, supporting a range of community, arts and tourism activities on the land in a coordinated manner. | Short | Commenced | Council supports artistic groups such as Adelaide Hills Ceramics and Sculptors@Crystal Lake to operate from Crystal Lake. More recent improvements at this land include a new public toilets, improved vehicle management and maintenance (resheeting) of the access road.
27 | Investigate activities or conservation initiatives that could be undertaken on the underutilised parts of the community land throughout the town | Short | Not Commenced
28 | Recognise Davenport Square as an important space for civic and cultural activities and continue to undertake improvements to the land in accordance with the Davenport Square Master Plan. | Short | Commenced | Over the years Council has supported the MCA who have been successful in winning grants to continue to make improvements to Davenport Square.
29 | Continue to recognise the Davis Road Reserve, the Night Paddocks, the Parklands Reserve and the cemetery land as important native vegetation conservation areas. | Ongoing | Commenced | Commenced through business as usual.
30 | Support the increased use of the Davis Road Reserve, the Night Paddocks, the Parklands Reserve and the cemetery land for passive recreation activities, through the establishment of well-signed designated walking trails. | Medium | Not Commenced
31 | Continue to support a range of community activities provided by local interest groups in the Macclesfield Institute to encourage and support improved social inclusion outcomes for the community. | Ongoing | Commenced | Council upgraded the kitchen at the Institute and as part of the mainstreet work created a paved forecourt in front of the building to help support the use of the area by the community. One example is the Macclesfield Market which uses this space.
32 | Support the community to manage and protect native vegetation conservation areas including Davis Road Reserve, the Night Paddocks, the Parklands Reserve, the cemetery land and creek lines in private ownership, liaising with the NRM Board to educate property owners on watercourse management. | Ongoing | Commenced | Commenced through business as usual.
33 | Work with the Primary School, church and community groups to identify opportunities to share their facilities for community use. | Short | Not Commenced
34 | Undertake a review of the most appropriate naming of reserves throughout the town to ensure they better reflect community sentiment. | Short | Not Commenced
35 | Continue to support the Macclesfield Recreation Grounds as a key destination for community and sporting facilities. | Ongoing | Commenced | Council supports local sporting teams through the provision of facilities and infrastructure working with the Recreation Ground management committee.
36 | Improve the efficiency and availability of storage solutions on the land by rationalising the use of buildings within the land and identify buildings and structures which could be consolidated and or removed where appropriate. | Medium | Not Commenced
37 | Provide disabled access to existing toilet facilities located within the change rooms on the eastern side of the oval. | Short | Not Commenced
38 | Resurface the southern three tennis courts to improve the playing surface. | Medium | Completed
39 | Extend the existing building to provide for women’s and umpire change rooms. | Medium | Not Commenced
40 | Provide a secure and continuous fence/barrier around the oval. | Medium | Not Commenced
41 | Investigate the potential for establishing passive recreation activities in this part of the land, including, picnic tables, nature play and a walking trail. | Short | Not Commenced
42 | Improve the facilities associated with Men’s Shed and Battunga Lions Club providing for better access to toilets and extending the existing building where required to better support the function of these clubs. | Short | Not Commenced
43 | Continue to support the use and function of the RSL Gardens, ensuring that suitable facilities are provided for visitors and events associated with this use. | Ongoing | Commenced | Commenced through business as usual.
44 | Support the community to undertake improvements to the Macclesfield Recreation Grounds in accordance with the Macclesfield Recreation Grounds Business Plan. | Ongoing | Commenced | Commenced through business as usual.
45 | Continue to recognise and support the Kidman Trail head on the land, providing and maintaining appropriate infrastructure to support this use. | Ongoing | Commenced | Commenced through business as usual.
46 | Provide a site for overnight RV accommodation, including the establishment of a dump point at a suitable location on the land close to existing infrastructure. | Short | Not Commenced | RV Park program not currently active. Alignment with key stakeholders did not support the establishment of a proposed RV Park at the Macclesfield Recreation Ground.
47 | Better recognise Lord Robinson Park as an import site for arts and culture, health and wellbeing and environmental conservation, encouraging increased use of the land by visitors and the community. | Medium | Commenced | Commenced through business as usual.
48 | Partner with community groups to develop Lord Robinson Park in accordance with the following concept plan. | Medium | Not Commenced
49 | Promote the increased use of the land for community and conservation activities providing opportunities where possible for environmental education initiatives. | Short | Not Commenced
50 | Prepare a Community Land Management Plan to better co-ordinate the various user groups on the land and to improve the efficiency of uses on the land. | Short | Not Commenced
51 | Prepare a management agreement with the Macclesfield Community Association to administer the various community uses on the land. | Short | Not Commenced
52 | Review the most appropriate service and maintenance levels for the land, identify potential for increased maintenance where possible. | Short | Completed | Council has reviewed and adjusted the maintenance service levels for this land.
53 | Brand and promote Macclesfield as a regional centre for arts and culture throughout the southern Mount Lofty Ranges, supporting local artists where possible. | Medium | Not Commenced
54 | Continue to support major community events which contribute to the local economy and support existing local businesses. | Ongoing | Commenced | Council continues to support local community events.
55 | Support the growth of local producers and emerging businesses and support initiatives which have an arts and cultural or environmental conservation focus. | Ongoing | Commenced
56 | Continue to provide support to local businesses by providing access to Council’s Economic Development Officer and linking the business community with education and training programs and government grants for small business. | Ongoing | Commenced | Council's Economic Development Officer regularly engages with businesses and provides support where required.
57 | Investigate the potential for developing land within the Deferred Urban Zones, including justification for any re-zoning, the most appropriate use of the land and the land’s capability for providing such uses. | Short | Commenced | Council has completed an internal review of the residential land supply within the existing urban residential areas to determine the demand for areas of additional residential development within the township. The initial review has determined that there is presently sufficient supply of residential land within the existing urban areas such that would not at this time necessitate the rezoning of land within the Deferred Urban Zone. This may change in the future. At this point in time, a Council-led Code amendment is not a priority but Council is supportive of a private Code amendment that looks to this issue.
58 | Investigate the potential for changes to existing residential development policy to encourage alternate and smaller living options close to the main street and existing services. | Short | Completed | Staff investigated the potential in the context of the Planning and Design Code but no further action is proposed to occur due to land ownership constraints.
59 | Investigate the on-going suitability and effectiveness of the Home Industry Zone policies, considering alternative development policy to more effectively provide for mixed uses activities within this zone. | Medium | Not Commenced
60 | Investigate the effectiveness of the existing Local Centre Zone policies, considering alternative policy to encourage a more broad range of commercial and residential development such as that within the Township Zone. | Medium | Completed | Staff investigated the potential in the context of the Planning and Design Code but no further action is proposed to occur due to land ownership constraints.
61 | Investigate a suitable location for the establishment of a Bio char facility within the Macclesfield led area. | Short | Commenced | Commenced through business as usual.
62 | Investigate the most appropriate zoning for the town’s conservation areas e.g. Conservation Zone rather than Open Space Zone. | Medium | Not Commenced
63 | Continue to recognise and support commercial development along the main street, ensuring that it continues to be the economic and service focal point of the town. | Ongoing | Commenced | The completion of the mainstreet upgrade work has been designed and delivered in collaboration with new and existing business owners to support the growth and development of local businesses and supporting local economic development.
64 | Continue to improve the pedestrian experience along the main street ensuring that footpaths, public seating, local art installations and landscaping that is both functional and attractive. | Medium | Completed | Council has now completed the main street upgrade consistent with masterplan.
65 | Complete a detailed design for improvements to the eastern side of the main street (Venables Street) which adequately reflect community expectations and which is cost effective to deliver. | Short | Completed | Construction now completed.
66 | Establish a program to secure funding to complete improvements to eastern side of the main street, including grant funding applications. | Short | Completed | Council was successful in securing Grant funding to help deliver the improvements to the eastern side of the mainstreet.
67 | Provide for opportunities to increase activity on the main street by providing spaces for on street dining and public seating. | Short | Completed | Construction now completed.
68 | Support events and activities which activate the street and increase activity along the street, including outdoor dining and community events. | Ongoing | Commenced | Business as usual.
69 | Undertake a review of existing street infrastructure (including kerb and gutter) and upgrade to a level of consistency within the confines of the township. | Medium | Not Commenced | Commenced through the Footpath Program.
70 | Educate property owners on best practice management of creek lines within private ownership. | Ongoing | Not Commenced
71 | Undertake a review of pedestrian footpaths within the township so as to inform potential for infrastructure upgrades in the context of already programmed and future proposed works. | Medium | Commenced | Commenced through the Footpath Program.
72 | Investigate demand and potential for the installation of street lighting adjacent the Primary School. | Medium | Not Commenced
73 | Investigate undertaking improvements to the roadside edge of Vernon Street adjacent the primary school e.g. kerb and water table. | Medium | Completed | Council constructed a new footpath to the school along Vernon Street.
74 | Review location of town limit speed zones to ensure consistency throughout the town e.g. Todd Street. | Short | Not Commenced