## Meadows
Action Number | Endorsed Action | Endorsed Timeframe | Status as of March 2025 | Comment
1 | Advocate and support the continued protection of heritage places, monuments and the Historic Conservation Area. | Ongoing | Completed | Successfully integrated through the South Australian Planning and Design Code.
2 | Celebrate indigenous and european heritage and culture of the area through initiatives such as interpretive signage, public art and the materials chosen for public realm improvements. | Ongoing | Not commenced | To be included within future projects.
3 | Continually inform and facilitate community information sessions on planning and development of Local Heritage Places and the Historic Conservation Area including accessing the Heritage Incentive Scheme. | Ongoing | Commenced | Ongoing through Council business as usual. Heritage Incentive Scheme continues to be an annual program offered by Council.
4 | Reinforce detached dwellings on large allotments, whilst investigating opportunities for housing diversity in appropriate locations (outside of heritage areas). | Ongoing | Completed | Successfully integrated through the South Australian Planning and Design Code.
5 | Encourage private property owners to improve their land and buildings in line with heritage objectives that have an interface with important public spaces. | Ongoing | Commenced | Heritage Incentive Scheme continues to be an annual program offered by Council.
6 | Support the continued development of the town in an integrated and planned approach. | Ongoing | Commenced | Ongoing through Council business as usual.
7 | Improve the appearance of township entrances and approaches. Develop gateway treatments that reflect the local sense of place and heritage. | Medium | Action transferred | To be undertaken in future stages of the Township Plan Entry Statements Program.
8 | Improve and promote the Meadows Heritage Walk. | Ongoing | Commenced | Ongoing through business as usual.
9 | Reinforce existing township boundaries. | Ongoing | Completed | Successfully integrated through the South Australian Planning and Design Code.
10 | Continue to support the role and function of community and sporting groups, acknowledging the important role they play to encourage social interaction and inclusion. | Ongoing | Commenced | Ongoing through Council business as usual.
11 | Continue to support local community events which provide an opportunity for the community to come together and which helps to cement the identity of the town and creates a sense of community. | Ongoing | Commenced | Ongoing through Council business as usual.
12 | Advocate for a broader range of in-home services to operate throughout the town so that the elderly and disabled can continue to remain within the Meadows community. | Short | Commenced | Ongoing through Council business as usual.
13 | Continue to provide transportation services for the elderly and disabled through Council’s Hills Community Transport program and advocate for improved public transport services. | Ongoing | Commenced | Ongoing through Council business as usual.
14 | Investigate changes to development plan policy which provide for smaller housing options throughout the town and which provides for aged and support care housing where appropriate to ensure that housing better caters for all residents. | Medium | Not commenced | Investigated and will not be progressed at this stage.
15 | Provide information to the Meadows community on the housing support services available throughout the district, connecting those experiencing housing difficulties with the appropriate services. | Short | Commenced | Ongoing through Council business as usual.
16 | Continue to provide facilities which cater for informal recreation activities to engage younger residents and support community groups which perform this role. | Ongoing | Commenced | Ongoing through Council business as usual.
17 | Where possible support the role, function and growth of the Meadows Primary School and the Meadows and District Kindergarten to continue to provide desirable local education options for the town. | Ongoing | Commenced | Ongoing through Council business as usual.
18 | Establish improved pedestrian links throughout the township, direct connectivity with Battunga Park from the recreation grounds and across Mawson Road. | Medium | Commenced | Footpath improvements to be prioritised and undertaken through the Footpath Program.
19 | Improve pedestrian crossing across Kondoparinga Road at the intersection of Mawson and Kondoparinga Road. | Short - Medium | Not commenced | Not commenced.
20 | Review footpath infrastructure on Mawson Road and undertake footpath upgrades where necessary to provide improved pedestrian access. | Medium | Commenced | Footpath improvements to be prioritised and undertaken through the Footpath Program.
21 | Advocate for improved public transport services and associated infrastructure for the township. | Ongoing | Commenced | Ongoing advocacy role by Council.
22 | Establish improved facilities for cyclists on Mawson Road and explore the opportunity for the provision of cycling lanes along Mawson Road. | Medium | Not commenced | To be considered within any future improvements.
23 | Investigate heavy vehicle movements within Meadows as to inform potential alternate routes for heavy vehicles. | Short | Not commenced | Initial internal review undertaken but no formal feasibility undertaken.
24 | Investigate and liaise with DIT regarding the potential for reduced speed limits within the Meadows Township. | Short | Not commenced | Initial review undertaken but no formal process begun.
25 | Investigate suitability of the existing school crossing on Mawson Road with DIT and implement upgrade if required. | Short | Commenced | Completed.
26 | Upgrade the Mawson / Battunga Road intersection and undertake streetscape upgrade works that includes on street car parking and Water Sensitive Urban Design elements. | Short | Commenced | Design completed, budget provided within 22/23 financial year, project on hold until DIT intervention finalised. Nottage Road improvements to commence 2023. Nottage Road improvements decoupled from this project and were completed in 2024. Council continue to advocate for this intersection upgrade as a priority.
27 | Maintain Battunga Park as the premier ‘all ages’ open space reserve within the township and as a key ‘stop-off ’ destination within the region and upgrade as part of Council’s renewal program. | Ongoing | Commenced | Ongoing through Council business as usual.
28 | Establish improved pedestrian links and direct connectivity with Battunga Park from the recreation grounds and south of Mawson Road. | Medium | Not commenced | To be scoped and actioned, budget permitting.
29 | Improve quality of the trail along Mawson Green linear reserve and connectivity to existing open space. | Medium | Not commenced | To be scoped and actioned, budget permitting.
30 | Investigate and improve the usability of Council land adjacent to the Memorial Hall and encourage community and tourist uses such as establishing a dog park or support the expansion of the existing kindergarten for example. Screening planting adjacent residential properties could be established in the short term. | Short - Medium | Not commenced | Not commenced.
31 | Investigate the potential to develop Meadows as a trails hub (cycling, horse riding, motorcycling). | Short | Not commenced | Not commenced.
32 | Investigate potential for enhancements to existing reserves including Michelmore Reserve to improve community usability while in the short term undertaking increased tree planting in reserves, creek lines and township entrances. | Ongoing | Not commenced | Being considered by Commuity Propoerty, subject to decision of Council and community land revocation.
33 | Support community projects linked to natural areas within Meadows and the surrounding hinterland. | Ongoing | Commenced | Ongoing through Council business as usual.
34 | Promote connectivity of the township to the nearby Kidman Trail and Heysen Trail (directional signage and way finding). | Ongoing | Not commenced | Not commenced.
35 | Improve provision of youth based play and recreation within existing reserves and open space. | Short - Medium | Not commenced | Not commenced.
36 | Work with the Meadows Recreation Ground Committee to investigate options and secure land for recreation ground and oval expansion into adjacent land to the north. | Short - Medium | Commenced | Council are in disucssions with potential purchasers regarding the potential to secure land to enable oval expansion. Seeking grant funding. Land acquisition completed and early works for an extended oval have been completed. Future redevelopment of the oval subject to budget commitment.
37 | Continue to promote and support the Meadows Recreation Oval as a key community recreation and event area within the township. | Ongoing | Commenced | Ongoing through Council business as usual.
38 | Investigate and if possible establish an RV Park on land within the Recreation Ground. | Short | Commenced | In budget, project commencing.
39 | Enhance and promote existing recreational facilities for increased community use and activation where possible and upgrade if and when required. | Ongoing | Commenced | Ongoing through Council business as usual.
40 | Investigate potential for recycled water irrigation within reserve areas. | Short | Not commenced | Not commenced.
41 | Provide additional landscaping in appropriate areas throughout the recreation ground as informed by a Landscape Concept Plan. | Ongoing | Not commenced | Preliminary investigations being undertaken.
42 | Formalise car parking adjacent to Brooks Street and around the surrounds of the oval and improve access arrangements in consultation with the Recreation Ground Committee and the Primary School. | Medium | Not commenced | Not commenced.
43 | If and when required undertake a review and needs analysis of existing recreation ground facilities to determine feasibility and potential for redevelopment. | Medium | Commenced | Not commenced. Subject to demonstration of need by stakeholders.
44 | Review current zoning provisions of the Mixed Use and Local Centre Zones so as to allow greater flexibility of employment land, tourism and agricultural industries. | Short | Completed | The South Australian Planning and Design Code allows for more flexibility of land use within the relevant more recent zoning.
45 | Investigate rezoning the Deferred Urban Zone to facilitate residential development. These investigations would also consider existing land supply within the Residential Zone. | Short | Commenced | Initial review undertaken but not prioritised.
46 | Promote the feasibility of an anchor retail tenant within the township in the short to medium term by creating policy conditions which support the development of a supermarket. | Short | Commenced | Previous Retail Analysis undertaken by Council. Ongoing strategic support for development applications within Meadows to cater for the identified demand.
47 | Investigate and promote short-term accommodation within the township with the aim of increasing overnight stays through implementation of an RV Park. | Ongoing | Commenced | Project commenced. Budget within 22/23 financial year.
48 | Develop and promote touring routes through the Adelaide Hills which connects to other towns and experiences in the region with an aim to increase overnight stays. | Ongoing | Commenced | Ongoing through Council business as usual.
49 | Continue to promote and grow existing events while seeking opportunities for smaller scale event growth. | Ongoing | Commenced | Ongoing through Council business as usual.
50 | Promote the formation of a Traders and Business Association in order to better promote the township, businesses and events within the town. | Ongoing | Not Commenced | Not commenced.
51 | Review the quality of the footpaths along the main street and implement upgrades where necessary noting that safety issues will be attended to as a priority. | Medium | Commenced | Infrastructure team have commenced a district wide audit. Improvements to be prioritied through the Footpath Program.
52 | Upgrade existing street furniture, lighting and provide a bus shelter along the main street with priority adjacent key land uses such as the Memorial Hall, recreation ground entrance and school. | Medium | Not Commenced | Subject to future budget commitment and priority.
53 | Undertake activation, beautification and landscaping infill (low lying and low maintenance planting) between existing street trees as informed by a Landscape and Streetscape Masterplan. | Ongoing | Not Commenced | Subject to future budget commitment and priority.
54 | Further promotion of street activation of the main street through provision of community art and events. | Ongoing | Not Commenced | Subject to future budget commitment and priority.
55 | Renew signage and way-finding of the main street at the Battunga/Mawson Roads intersection and township entrances. | Short | Commenced | Subject to future budget commitment and priority. To be included in Mawson/Battunga Intersection upgrade.
56 | Undertake a review of existing stormwater management within the township. | Short | Not Commenced | Not commenced.
57 | Educate property owners on best practice management of creek lines within private ownership. | Ongoing | Commenced | Ongoing through Council business as usual.
58 | Undertake a review of existing kerb, gutter and pedestrian footpaths within the township as to inform potential for infrastructure upgrades in the context of already programmed and future proposed works. | Medium | Not Commenced | District wide audit completed. Improvements to be prioritised through the Footpath Program. Most notably the Nottage Road upgrade currently under construction will provide improved footpaths in the immediate locality.
59 | Investigate the potential to increase recycled water infrastructure within the Township. | Medium | Not Commenced | Not commenced.
60 | Continue working with the CFS to ensure Bushfire Management Plans are up-to-date. | Ongoing | Commenced | Ongoing through Council business as usual. Councils Fire to Flourish team provided community support until its recent project completion.
61 | Improve localised stormwater management on Battunga Road within the township. | Short - Medium | Not Commenced | Not commenced.