## Nairne
Action Number | Endorsed Action | Endorsed Timeframe | Status as of March 2025 | Comment
1.1 | Develop an area wide tourism plan recognising cultural heritage relationships and historic linkages to adjacent Hills and Murraylands regions. | Short
1.2 | Ensure cultural relationships with the Peramangk people are acknowledged and enhanced. | Short | Action transferred | Community Development.
1.3 | Prepare design and management guidelines that recognise the interface between agricultural land uses and urban activity – ensure ongoing viability of agricultural land continues – recognise differing locations and needs. | Medium
1.4 | Obtain independent analysis of rural zoned land within the township boundary and adjacent rural Mt. B zoned land to confirm suitability for ongoing rural/agricultural land use activity. | Long | Not commenced
1.5 | Retain Nairne as an independent township but recognise the need to connect to other adjacent local and regional services and facilities (particularly regional trails and recreation networks), and that Nairne also potentially provides services for residents in nearby smaller towns. | Medium | Completed | Through the policies of the Planning and Design Code, specifically the township and surrounding area zonings and extent of the EFPA, as directed through the PDI Act and inter urban breaks noted in the Greater Adelaide Regional Plan.
1.6 | Review current Development Plan zoning and policy to address existing zoning on western side of Woodside road recognising potential for further development opportunities. | Short
1.7 | Review current Council policy to enhance environmental and biodiversity opportunities including creek management, flood mitigation and watercourse rehabilitation incorporating water sensitive urban design solutions and ensure bushfire management issues are addressed, particularly in relation to new development proposals. | Medium
1.8 | Continue to advocate strongly for installation of new Freeway access. | Short | Ongoing | Ongoing through Council business as usual.
2.1 | Prepare urban design guidelines to reinforce residential character issues in each of the three precincts. | Medium
2.2 | Investigate services necessary to support Nairne population including community needs and recreation, and utility services, determine priorities and plan for implementation over time – major advocacy role given variety of service providers. | Medium
2.3 | Establish an integrated network of trails and other connections in open space corridors (including creek line corridors) that link existing Council owned and managed reserves and provide linkages locally and regionally and to the town centre. | Medium | Action transferred | To be taken up within the Open Space Strategy.
2.4 | Undertake a review of current Development Plan policy to ensure delivery of desired urban design outcomes and a connected and high quality residential environment relevant to Nairne in particular the area west of Woodside Road and south of the railway line. Include options for affordable housing, housing for the aged, housing for disadvantaged groups throughout the township. | Short
2.5 | Consider the preparation of overall landscape plan for township that embraces the ‘walkable community’ philosophy and encourages public streetscapes as unique identifiers for each of the precincts. | Long | Action transferred | To be taken up within the Open Space Strategy.
2.6 | Prepare options that provide coordinated and integrated traffic solutions across all precincts as development proceeds. | Medium
2.7 | Negotiate with DPTI regarding extensions to current public transport services as the town develops and particularly services to the south of the Main Road including newly zoned residential land (MDPA). | Long | Action transferred | As per Council's Advocacy Plan.
2.8 | Review current Development Plan policy in relation to rural living areas ensuring policy is clear in terms of ongoing function and land use activity. | Short
3.1 | Review Development Plan to ensure new development road networks/proposals, provide integrated linkage to the current road systems, do not concentrate traffic flows at unacceptable locations, and contribute positively towards maintenance of town character. | Medium
3.2 | Investigate performance of key junctions and where appropriate, prepare plans for traffic management improvements that can be implemented over time as priorities, finances and demands dictate – continue to negotiate/advocate with DPTI as necessary. | Medium | Action transferred | As per Council's Integrated Transport Plan
3.3 | Investigate the function and performance of key council managed roads and prepare local area traffic management improvement plans as necessary for implementation over time as priorities, finances and demands permit. This should also consider changing the function of specific roads where the future function and performance issues are unable to be resolved due to physical constraints of the local area. | Long
3.4 | Investigate measures along North Road aimed at improving safety and reducing the use of the road as a ‘short cut’ connection between Woodside Road and Nairne east. Prepare plans for implementation over time as priorities, finance and demands permit. | Short
3.5 | Continue to advocate strongly for the installation of new freeway access ramps at Bald Hills Road. | Short | Commenced | Ongoing through Council business as usual.
3.6 | Continue to negotiate/strongly advocate, for traffic management improvements at the junctions of Saleyard and Woodside Roads with Princes Highway (DPTI, developers and landowners). | Medium | Commenced | Ongoing through Council business as usual.
3.7 | Negotiate/advocate with DPTI for extended public transport services (evening) and extensions to the public transport network to south of township as land in that area develops. | Long | Commenced | Ongoing through Council business as usual.
3.8 | Investigate and continue to advocate to DPTI for ‘park n ride’ services to encourage reduced motor vehicle dependency. | Medium | Commenced | Ongoing through Council business as usual.
3.9 | Maintain a strong focus for accessibility to the town centre and develop streetscaping options (township wide) that reinforce the town character and provide local area and street identity. | Long | Action transferred | To be taken up within the Open Space Strategy.
3.10 | Consider the preparation of an overall integrated vehicle movement network plan that results in improved connectedness throughout the town and defines parking opportunities which can be implemented over time and as priorities, finances and demands permit. | Long | Action transferred | As per Council's Integrated Transport Plan
4.1 | Review the Development Plan to ensure any new proposals provide appropriate levels of open space and that pedestrian and cycle linkages connect to and integrate with the local and wider networks. | Medium | Action transferred | To be taken up within the Open Space Strategy.
4.2 | Develop options for streetscape, footpath, seating and street lighting improvements that create an integrated approach to people movement and provide a focus for users eg town centre, recreation spaces, public transport. | Medium | Action transferred | To be taken up within the Open Space Strategy.
4.3 | Using the recently completed Council Recreation Needs analysis and Open Space Study as a guide, determine the future use associated with Council owned land and where necessary prepare landscaping plans that can be initiated over time and as funding and demand permit. | Long | Action transferred | To be taken up within the Open Space Strategy.
4.4 | Define locations where Council endorsed Trails Plan for Mt Barker Littlehampton and Nairne and the wider regional trails network provides key linkage points to the Nairne township. – in particular Bald Hills Road, Princes Highway, Woodside Road, Sydney Road, Summit Road, Little Dublin East Road. | Long | Action transferred | To be taken up within the Open Space Strategy.
5.1 | Obtain further independent specialist economic development advice to understand economic drivers of the township and surrounding area (both locally and regionally). | Short | Action transferred | As per Council's Economic Development Strategy 2022-2027.
5.2 | Determine the potential (as part of specialist economic development advice) for support for improved retail shopping (including retail supermarket) and other commercial and business services within the Main Street. | Short
5.3 | Prepare detailed streetscape plans addressing car parking, traffic flow and management, landscaping and street furniture and key intersections along Main Street. | Medium
5.4 | Continue to advocate for undergrounding of powerlines in Main Street. | Short | Commenced | Ongoing through Council business as usual.
5.5 | Prepare plans for the upgrade of the reserve area at Jeffrey Street, which aims to improve facilities, relocate one existing tennis court, incorporate Cockburn Street, improve toilet facilities and detail alternative pavement treatments so as to provide a central meeting place and focus for the town centre. Implement as priorities, finances and other demands dictate. | Medium
5.6 | Consider the opportunity for council to provide ‘heritage’ grant funding directed towards buildings/refurbishment in Main Street environment. | Short | Ongoing | Ongoing through Council's business as usual operations in administration of Heritage Incentive Scheme (available through application to Council).
5.7 | Advocate for State/Federal grant funding supporting heritage and people for places monies. | Short
5.8 | Review Development Plan Policy and zoning to encourage integrated mixed use development, and redevelopment, that adds, vibrancy, identity and flexibility to the Main Street built form and design and maintains current historic urban design cues. | Short
5.9 | Consider potential ‘township zone’ or ‘mixed use zone’ as expressed in the Better Development Plan for the whole of the ‘town centre area’ (refer map 10). | Short
5.10 | Prepare guidelines to encourage consistency in future development and appropriate recognition of current historic built form, materials, and setbacks. | Medium
5.11 | As part of a traffic management analysis for the town reinforce opportunities for improved connections, pedestrian, cycle, and vehicle to the business core, reinforce these main linkages with streetscape identity and paving materials. | Medium
5.12 | Advocate for improvements to current public transport services – in particular, presence, frequency of services and connections with Main Street activities. | Long | Action transferred | As per Council's Advocacy Plan.
5.13 | Investigate potential for Council to provide additional or improved services within the core area including Council community services, halls, and facilities. | Medium
5.14 | Advocate for Government service improvements and support and their location in the core area. | Long
5.15 | Investigate tourism opportunities and the role and relationship of Nairne to Mount Barker Summit – Aboriginal heritage mapping and a cultural focus for Nairne. | Long
5.16 | Identify opportunities for Council to acquire land or use current Council owned land to support re development of the Main Street as a “focus” for the township. | Long
6.1 | Prepare an overall Heritage precinct plan (using Council Heritage Architect) that reinforces the built form and function of older residential buildings and the Railway Station. Include streetscape design, current landscape and safety issues and details of the potential future land uses appropriate for the area. | Long
6.2 | Advocate for State, Federal, and other local heritage grant opportunities and ensure retention of Council Heritage Architect. | Short
6.3 | Consider the potential for Council to resume ownership of Railway Station buildings and surrounds and consider options for future redevelopment to provide increased heritage, tourist, community and possible business and park n ride focus. | Long
6.4 | Review Development Plan Policy to ensure more appropriate development that relates to and respects the historic nature of built form and land division pattern of the precinct. | Short | Completed | Comments provided to the State government prior to the introduction of the Planning and Design Code and PDI Act.
6.5 | Continue to encourage local community groups in their use of the Railway Station facilities and determine levels of ongoing support (both Council and other agencies) for such groups. | Long |  | Ongoing through Council business as usual.
7.1 | Undertake a review of current Development Plan policy to ensure delivery of desired urban design outcomes and a connected and high quality residential environment that reinforces and supports the town character. Determine the appropriateness of various types of residential development and hammerhead land division. | Short |  | Council has successfully embedded this priority within the Planning and Design Code.
7.2 | Prepare urban design guidelines that reinforce residential character issues, particularly along the Main Street frontage and adjacent to the rail corridor and creek lines. | Medium
7.3 | Develop an integrated network of trails and other connections in open space corridors (including creek line corridors) that link existing Council owned and managed reserves and provide linkages to the town centre. | Long | Action transferred | See Open Space Strategy.
7.4 | Prepare an overall landscape plan for the precinct that embraces the ‘walkable community’ philosophy and encourages public streetscapes as unique identifiers. | Medium |  | Possibly accommodated within Council's Open Space Strategy.
7.5 | Develop options that provide coordinated and integrated traffic solutions across all precincts as development proceeds. | Long | Ongoing | Ongoing through Council business as usual and administration of the PDI Act through development assessment role.
7.6 | Identify opportunities for Council to purchase additional land to improve management of creek corridors and increase safety at Main Road crossing points. | Long
8.1 | Review Development Plan zoning to provide an integrated approach to the development of both precincts. Zoning review should embrace the opportunity to provide increased services to the Nairne community that are not available elsewhere given fragmented land ownership and small lot sizes within the Main Street precinct. | Short | Completed | Comments provided to the State government prior to the introduction of the Planning and Design Code and PDI Act.
8.2 | Obtain independent specialist retail analysis and advice in relation to the location of retail supermarket facilities for Nairne – and when and where appropriate initiate zoning change to accommodate change. Analysis to also provide information on Main Street economic development potentials and impacts which ultimately influence zoning policy. Ensure the Main Street remains a focus for the Nairne community. | Short | Completed | Release of retail review and other related materials (2013).
8.3 | Continue to advocate and negotiate with DPTI and those proposing development for traffic improvements – in particular Woodside Road, Princes Highway and Saleyard Road junctions. | Short |  | Ongoing through Council business as usual.
8.4 | Ensure pedestrian/cycle linkages provide access to the wider trails network and local open space and other town centre precincts – particularly heritage and main street core. | Long | Action transferred | To be taken up within the Open Space Strategy.
8.5 | Review and consider current light industrial zoning and activity within the both precincts and consider alternative location options to maintain local employment opportunity. Note: site owners to undertake relevant environmental assessments and initiate appropriate site remediation measures to accommodate new land use activity. | Short
8.6 | Continue to advocate to DPTI for ‘park n ride’ opportunities (potentially in the western precinct). | Medium |  | Ongoing through Council business as usual.
8.7 | Negotiate/advocate with DPTI in relation to landscaping on Woodside Road and Princes highway contributing to unique gateway/entry points. | Long
8.8 | Develop an emergency management plan for the Nairne community relating to potential “blocking” or ‘closure’ of the interstate railway crossing point on Woodside Road and for other emergency situations eg. Bush fire. | Medium
9.1 | Review Council's Community Needs and Recreation Needs analysis as they apply to the Nairne township and prepare plans to be implemented over time as priorities, finances and demands permit – as a first priority, the recommendations contained in the “Nairne and District Sporting Complex – Strategy and Concept Plan” dated November 2012. | Medium
9.2 | Consider the location of facilities in a way that supports the town centre environment and in an integrated way that is based upon sharing spaces rather than providing individual facilities. | Medium
9.3 | Investigate the opportunity to locate outreach Council services and administration within the township. | Long
9.4 | Develop an ‘advocacy and brokerage’ approach to the delivery of services working closely with service providers and relevant agencies and proposers of development. | Short
9.5 | Investigate support funding opportunities and alternative funding models for the provision of services and facilities. | Long
9.6 | Review the current Council CWMS services and determine the need for improvement(s), and any potential wastewater reuse and recycling locally and beyond the township. | Short | Commenced | For consideration by Wastewater Business Development officer.
9.7 | Review the Council Development Plan to ensure flexibility in the provision of community support services and facilities – in particular housing affordability, variety and accommodation types. | Short
9.8 | Complete an inventory of Council owned land and Council service provision relative to Nairne and prepare a plan that responds to the changing demands of a growing community that can be implemented over time as priorities, finances and demands permit. | Long
10.1 | Council to encourage and support the community involvement in the monitoring and future development of the Nairne township via volunteer groups and organisation and/or the Community Reference Group. | Short | Ongoing | As per the Community Development Lead Strategy.
A | Upgrade main street (not in plan). | Short
B | Village Green construction (not in plan). | Short | In progress | Stage 1 (Village Green and Heritage Garden) complete Stage 2 (Play and Youth) complete Stage 3 (Recreation and Cultural Garden) yet to commence